## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-03-02 | Azure compute usage dataset had missing values during preprocessing | Sprint 1 | Backend Team | Functional | Cleaned dataset and handled null values | 2026-04-02 | Closed | Verified successfully
2 | 2026-06-02 | External market demand dataset format inconsistent | Sprint 2 | Backend Team | Data Validation | Unified schema and corrected column formats | 2026-07-02 | Closed | Performance improved
3 | 2026-12-02 | Lag feature generation produced incorrect demand values | Sprint 2 | Frontend Team | Algorithmic | Fixed lag variable calculation in feature engineering | 2026-02-13 | Closed | Tested and verified
4 | 18/02/2026 | Feature engineering pipeline failed for seasonal flags | Sprint 2 | Backend Team | Data Processing | Updated preprocessing script and validated time features | 26/02/2026 | Closed | ARIMA model tuned and stabilized
5 | 25/02/2026 | ARIMA model producing unstable forecast values | Sprint 3 | Backend Team | Model Training | Tuned model parameters and retrained model | 19/03/2026 | Closed | XGBoost model performance improved
6 | 2026-03-03 | XGBoost model showing high RMSE error | Sprint 3 | Frontend Team | Algorithmic | Improved feature selection and retrained model | 2026-04-03 | Closed | User-friendly validation added
7 | 2026-10-03 | Forecast API not returning prediction results correctly | Sprint 3 | Backend Team | Integration | Fixed API endpoint logic and response format | 2026-11-03 | Closed | Dashboard integration working correctly
8 | 2026-03-15 | Dashboard not updating forecast results in real time | Sprint 4 | Frontend Team | Integration | Implemented auto refresh and API data binding | 2026-03-16 | Closed | Graph sync issue resolved
9 | 2026-03-20 | Azure deployment pipeline failing during model deployment | Sprint 4 | Backend Team | Deployment | Fixed deployment configuration in Azure ML | 2026-03-21 | Closed | Azure deployment pipeline fixed
10 | 2026-03-25 | Capacity planning dashboard showing delayed data updates | Sprint 4 | Frontend Team | Performance | Optimized API calls and caching mechanism | 2026-03-26 | Closed | Dashboard performance optimized